## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | DEPARTMENT OF EDUCATION - SDO PUERTO PRINCESA CTY Procurement Monitoring Report as of JULY 1 TO DECEMBER 30, 2021
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| CY 2021 Repair of Classrooms | [19 empty] | SGOD | NO | Competitive Bidding | 2021-02-06 | 6/15 - 7/5/2021 | 6/22/2021 | 2021-05-07 | 2021-05-07 | 2021-12-07 | 7/28-8/2/2021 | 2021-05-08 | 2021-06-08 | 2021-06-08 | 2021-09-08 | Nov. 9. 2021 | Nov. 9, 2021 | GoP | 4290385.51 |  |  | 3168710.23 |  |  | COA, PICE | 6/18/2022 | 2021-01-07 | 2021-01-07 |  |  | 2021-08-11
| CY 2020 Last Mile School Program | [19 empty] | SGOD | NO | Competitive Bidding | 6/22/2021 | 7/27-8/16/2021 | 2021-03-08 | 8/16/2021 | 8/16/2021 | 8/17/2021 | 8/31-9/6/2021 | 2021-10-09 | 9/13/2021 | 9/13/2021 | 9/14/2021 | June 18,2022 |  | GoP | 19.185.222.89 |  |  | 17695964 |  |  | COA, PICE | 7/31/2021 | 2021-12-08 | 2021-12-09
| CY 2021 Repair of Classrooms at Sta. Monica HS | [19 empty] | SGOD | NO | Competitive Bidding | 2021-09-11 | 11/24-112/15/2021 | 2021-03-12 | 12/15/2021 | 12/15/2021 | 12/16/2021 | 12/23/2021 | 12/24/2021 | 12/27/2021 | 12/27/2021 | 12/28/2021 | March 8. 2022 | March, 2022 | GoP | 1256788.67 |  |  | 1254870.47 |  |  | COA, PICE | 2021-01-12 | 2021-10-12 | 2021-10-12 |  |  | 2022-03-01
| CY 2020 Last Mile School Program in Public Elementary School - Construction of School Fence at Nasuduan ES | [19 empty] | SGOD | NO | NP-53.4 Adjacent or Contiguous | 2021-09-12 | [6 empty] | 12/15/2021 | 12/22/2021 | 12/22/2021 | 12/23/2021 | June 18, 2022 |  | GoP | 1335595.95 |  |  | 1335595.95 |  |  | COA, PICE
| Office Supplies and Consumables for the Provision of Learning Resources on the Implementation of the BE-LCP for the Printing of 3rd and 4th Quarter (Kto12) in EPP, TLE, and SHS SY 2020-2021 | [19 empty] | CID | NO | Competitive Bidding | 2021-06-04 | 5/4-5/24/2021 | 2021-10-05 | 2021-02-06 | 2021-02-06 |  | 2021-04-06 | 2021-08-06 | 2021-09-06 | 2021-09-06 | 2021-10-06 |  |  | GoP | 6038471 |  |  | 3575630.24 |  |  | COA, PPC Chamber of Commerce | 2021-06-05 | 5/31/2021 | 5/31/2021
| Office Supplies and Consumables for the Printing of Kindergarten Materials as Provision of Learning Resources in the Implementation of BE-LCP | [19 empty] | CID | NO | Competitive Bidding | 2021-02-06 | 6/4-6/22/2021 | 2021-09-06 | 6/22/2021 | 6/22/2021 |  | 6/24/2021 | 6/28/2021 | 6/30/2021 | 6/30/2021 | 2021-05-07 |  | 2021-03-08 | GoP | 1055785 |  |  | 824573.4 |  |  | COA, PPC Chamber of Commerce | 2021-04-06 | 6/17/2021 | 6/17/2021 |  |  | 2021-02-08
| Office Supplies and Consumables for the Provision of Learning Resources in the Implementation of BE-LCP for the Printing of 4th Quarter | [19 empty] | CID | NO | Competitive Bidding | 2021-02-06 | 6/4-6/22/2021 | 2021-09-06 | 6/22/2021 | 6/22/2021 |  | 6/24/2021 | 6/28/2021 | 6/30/2021 | 2021-02-07 | 2021-05-07 |  |  | GoP | 4373885 |  |  | 3381100 |  |  | COA, PPC Chamber of Commerce | 2021-04-06 | 6/17/2021 | 6/17/2021
| Office Supplies and Consumables for the Provision of Learning Resources per Joint Memorandum DM-OUCI-2021-044 under the BE-LCP | [19 empty] | CID | NO | Competitive Bidding | 2021-09-06 | 6/15-7/5/2021 | 6/22/2021 | 2021-05-07 | 2021-05-07 |  | 2021-06-07 | 2021-08-07 | 2021-12-07 | 2021-12-07 | 7/14/2021 |  |  | GoP | 1549765 |  |  | 1280490 |  |  | COA, PPC Chamber of Commerce | 2021-01-07 | 2021-01-07 | 2021-01-07
| Regular Office Supplies & Consumables for the Provision of Learning Resources in the Implementation of BE-LCP FY 2021 | [19 empty] | CID | NO | Competitive Bidding | 2021-05-07 | 7/9 -7/27/2021 | 7/14/2021 | 7/28/2021 | 7/28/2021 |  | 2021-03-08 | 2021-06-08 | 2021-09-08 | 2021-09-08 | 2021-10-08 |  | 8/17/2021 | GoP | 5315360 |  |  | 3477760 |  |  | COA, PPC Chamber of Commerce | 2021-09-07 | 7/23/2021 | 7/23/2021 |  |  | 8/16/2021
| Regular Office Supplies & Consumables for the Provision of Learning Resources in the Implementation of BE-LCP FY 2021 | [19 empty] | CID | NO | Competitive Bidding | 2021-05-07 | 7/9-7/27/2021 | 7/14/2021 | 7/28/2021 | 7/28/2021 | 7/28-7/30/2021 | 2021-02-08 | 8/20/2021 | 8/23/2021 | 8/23/2021 | 8/25/2021 |  |  | GoP | 1693385 |  |  | 1088745 |  |  | COA, PPC Chamber of Commerce | 2021-09-07 | 7/23/2021 | 7/23/2021
| Project RACOONS | [19 empty] | OSDS | NO | Competitive Bidding | 7/21/2021 | 9/7-9/14/2021 | 9/13/2021 | 9/27/2021 | 9/27/2021 |  | 9/28/2021 | 9/30/2021 | 2021-01-10 | 2021-01-10 | 2021-04-10 |  |  | GoP | 1000000 |  |  | 998910 |  |  | COA | 2021-08-09 | 9/23/2021 | 9/23/2021
| Supply and Delivery of Medicine, Medical Supplies and Equipment for the New Normal Set-up for Minimum Health Standards as additional MOOE allocation for COVID-19 in the Division Office and Public Schools | [19 empty] | SGOD | NO | Competitive Bidding | 7/21/2021 | 8/24-9/13/2021 | 8/31/2021 | 9/13/2021 | 9/13/2021 | 9/14-9/17/2021 | 9/20-24/2021 | 9/28/2021 | 9/30/2021 | 9/30/2021 | 2021-01-10 |  |  | GoP | 8922765 |  |  | 6399330 |  |  | COA | 8/26/2021 | 2021-08-09 | 2021-08-09
| Supply and Delivery of Office Suplies, Other Equipment and Consumables for the Provision of Q1 and Q2 Learning Resources of SY 2021-2022 under the Implementation of BE-LCP) | [19 empty] | CID | NO | Competitive Bidding | 9/13/2021 | 9/16-10/5/2021 | 9/22/2021 | 2021-08-10 | 2021-08-10 |  | 2021-11-10 | 10/14/2021 | 10/19/2021 | 10/19/2021 | 10/21/2021 |  |  | GoP | 8562703 |  |  | 6557680 |  |  | COA | 9/17/2021 | 2021-04-10 | 2021-04-10
| Supply and Delivery of Nutritious Food Products and Commercial Milk Component for the Implementation of the School based Feeding Program (SBFP) for SY 2021 | [19 empty] | SGOD | NO | Competitive Bidding | 9/20/2021 | 9/30-10/19/2021 | 2021-08-10 | 10/19/2021 | 10/19/2021 | 10/20/2021 | 10/20/2021 | 10/22/2021 | 10/25/2021 | 10/25/2021 | 20/26/2021 |  |  | GoP | 12264540 |  |  | 11842281 |  |  | COA | 2021-04-10 | 10/14/2021 | 10/14/2021
| Provision of Learning Resources on the Implemenation of BE-LCO for the Printing of 3rd and 4th Quarter (Kto12) in EPP, TLE, ad SHS SY 2020-2021 | [19 empty] | CID | NO | Competitive Bidding | 9/20/2021 | 9/30-10/19/2021 | 2021-08-10 | 10/19/2021 | 10/19/2021 | 10/20/2021 | 10/20/2021 | 10/22/201 | 10/25/2021 | 10/25/2021 | 10/26/2021 |  |  | GoP | 2462640.76 |  |  | 2354000 |  |  | COA | 2021-04-10 | 10/14/20221 | 10/14/2021
| Supply and Delivery of Office Supplies and Consumables for the Provision of Instructional Materials Printing under the Imlementation of BE-LCP for Quarters I and II | [19 empty] | CID | NO | Competitive Bidding | 9/20/2021 | 9/30-10/19/2021 | 2021-08-10 | 10/19/2021 | 10/19/2021 | 10/20/2022 | 10/20/2022 | 10/22/202 | 10/25/2022 | 10/25/2022 | 10/26/2022 |  |  | GoP | 2574465 |  |  | 2189160 |  |  | COA | 2021-04-10 | 10/14/2021 | 10/14/2021
| Supply and Delivery of Office Supplies, Equipment and Consumables for the Provision of Learning Resources in the Implementation pf bE-LCP | [19 empty] | CID | NO | Competitive Bidding | 2021-08-10 | 10/19-11/9/2021 | 10/25/2021 | 2021-09-11 | 2021-09-11 | 11/0/2021 | 11/11-12/2021 | 11/19/2021 | 11/22/2021 | 11/22/2021 | 11/23/2021 |  |  | GoP | 1837525 |  |  | 1537480 |  |  | COA | 10/21/2021 | 2021-04-11 | 2021-04-11
| Supply and Delivery of Office Supplies, and Consumables for the Provision of Learning Resources in the Implementation of BE-LCP | [19 empty] | CID | NO | Competitive Bidding | 10/28/2021 | 11/1-11/22/2021 | 2021-09-11 | 11/22/2021 | 11/22/2021 | 11/23/2021 | 11/23-24/2021 | 11/26/2021 | 11/29/2021 | 11/29/2021 | 2021-01-12 |  |  | GoP | 2005079 |  |  | 2,002,456,75 |  |  | COA | 2021-04-11 | 11/18/2021 | 11/18/2021
| Supply and Delivery of Office Supplies and Consumables to used for SBFP for SY 2021-2022 | [19 empty] | SGOD | NO | Competitive Bidding | 2021-09-11 | 11/17-12/9/2021 | 11/24/2021 | 2021-09-12 | 2021-09-12 | 2021-10-12 | 2021-10-12 | 12/14/2021 | 12/15/2021 | 12/15/2022 | 12/16/2021 |  |  | GoP | 1058500 |  |  | 1057235 |  |  | COA | 11/19/2021 | 2021-06-12 | 2021-06-12
| Supply and Delivery of Commercial Milk for the Milk Feeding Component of the School Based Feeding Program for the Last Mile Schools under the FY 2020 GAA | [19 empty] | SGOD | NO | NP-53.9 - Small Value Procurement | 2021-05-07 | 7/27-8/2/2021 | 2021-03-08 | 2021-03-08 | 2021-03-08 |  | 2021-05-08 | 8/10/201 | 2021-11-08 | 2021-12-08 | 2021-12-08 |  |  | GoP | 652320 |  |  | 396828 |  |  | COA |  |  | 7/27/2021
| Supply and Delivery of Meals and Snacks for the conduct of Development and Quality Assurance of Project DREAM (Digitized Resources in Education for Applicable Modality) on Learning Resources Across Subject Areas on August 4-6 and 9-13, 2021 | [19 empty] | CID | NO | NP-53.9 - Small Value Procurement | 2021-05-07 | 7/10-7/16/2021 | 7/16/2021 | 7/16/2021 | 7/16/2021 |  | 7/22/2021 | 7/27/2021 | 7/28/2021 | 7/29/2021 | 7/30/2021 |  |  | GoP | 400000 |  |  | 399400 |  |  | COA |  |  | 2021-10-07
| Supply and Delivery of Common Use Supplies and Consumables for the Schools Division of Puerto Princesa City for the 3rd Quarter of CY 2021 | [19 empty] | OSDS | NO | NP-53.9 - Small Value Procurement | 7/30/2021 | 8/8-8/16/2021 | 8/16/2021 | 8/16/2021 | 8/16/2021 |  | 8/16/2021 | 8/23/2021 | 8/24/2021 | 8/24/2021 | 8/25/2021 |  | 2021-08-09 | GoP | 374715 |  |  | 284250 |  |  | COA |  |  | 2021-08-08 |  |  | 2021-06-09
| Suppply and Delivery of Office Supplies, Medicine, Fogger & other consumables for the use of PPC Division for the 2nd Quarter of CY 2021 | [19 empty] | OSDS | NO | NP-53.9 - Small Value Procurement | 2021-02-06 | 6/15-6/21/2021 | 6/22/2021 | 6/22/2021 | 6/22/2021 |  | 2021-01-07 | 2021-05-07 | 2021-06-07 | 2021-06-07 | 2021-08-07 |  |  | GoP | 368430 |  |  | 367220 |  |  | COA |  |  | 6/15/2021
| Suppply and Delivery of Regular Office Supplies and Consumables for the Printing of K to 12 materials in the provision of Learning Resources in the Implementation of BE-LCP | [19 empty] | CID | NO | NP-53.9 - Small Value Procurement | 2021-09-06 | 6/15-6/21/2021 | 6/22/2021 | 6/22/2021 | 6/22/2021 |  | 6/23/2021 | 6/25/2021 | 6/28/2021 | 6/28/2021 | 6/29/2021 |  | 2021-05-08 | GoP | 766740 |  |  | 761820 |  |  | COA |  |  | 6/15/2021 |  |  | 2021-04-08
| Printng of Self Learning Modules (SLM) for the 4th Quarter as Provision of Learning Resoures in the Implementation of BE-LCP SY 2020-2021 | [19 empty] | CID | NO | NP-53.9 - Small Value Procurement | 9/20/2021 | 9/24-9/30/2021 | 2021-08-10 | 2021-08-10 | 2021-08-10 |  | 2021-11-10 | 10/13/2021 | 10/14/2021 | 10/14/2021 | 10/15/2021 |  |  | GoP | 992598 |  |  | 644459 |  |  | COA |  |  | 9/24/2021
| Provision of Learning Resources in the Implementation of the BE-LCP | [19 empty] | CID | NO | NP-53.9 - Small Value Procurement | 9/20/2021 | 9/24-9/30/2021 | 2021-08-11 | 2021-08-10 | 2021-08-10 |  | 2021-11-11 | 10/13/2022 | 10/14/2022 | 10/14/2022 | 10/15/2022 |  |  | GoP | 269210 |  |  | 183210 |  |  | COA |  |  | 9/24/2021
| Printing of Kindergarten Materials as Provision of Learning Resourcces on the Implementation of the Basic Education Learning continuity Plan (BE-LCP) | [19 empty] | CID | NO | NP-53.9 - Small Value Procurement | 9/20/2021 | 9/24-9/30/2022 | 2021-08-12 | 2021-08-10 | 2021-08-10 |  | 2021-11-12 | 10/13/2023 | 10/14/2023 | 10/14/2023 | 10/15/2023 |  |  | GoP | 231085 |  |  | 158925 |  |  | COA |  |  | 9/24/2021
| Supply and Delivery of Office Supplies and Consumables as Provision of Learning Resources in the Implementation of BE-LCP | [19 empty] | CID | NO | NP-53.9 - Small Value Procurement | 2021-08-10 | 10/13-10/19/2021 | 10/19/2021 | 10/19/2021 | 10/19/2021 |  | 10/22/2021 | 10/25/2021 | 10/26/2021 | 10/26/2021 | 10/27/2021 |  |  | GoP | 604600 |  |  | 400400 |  |  | COA |  |  | 10/13/2021
| Supply and Delivery of Office Suuplies and Consumables including Multivitamins and other medical supplies for Alternative Learnng System Program Suuport Fund (ALS PSF) | [19 empty] | CID | NO | NP-53.9 - Small Value Procurement | 10/19/2021 | 10/21/-10/28/2021 | 10/28/2021 | 10/28/2021 | 10/28/2021 |  | 10/29/2021 | 2021-03-11 | 2021-04-11 | 2021-04-11 | 2021-05-11 |  |  | GoP | 508650 |  |  | 384091.5 |  |  | COA |  |  | 10/21/2021
| Supply and Delivery of Office Supplies and Consumables for the Printing of Self Learning Modules (SLMs) for the 4th Quarter as Provision of Learning Resources on the Implementation of BE-LCP | [19 empty] | CID | NO | NP-53.9 - Small Value Procurement | 10/25/2021 | 11/1/-11/5/2021 | 2021-09-11 | 2021-09-11 | 2021-09-11 |  | 2021-11-11 | 11/15/2021 | 11/16/2021 | 11/16/2021 | 11/17/2021 |  |  | GoP | 348210 |  |  | 298500 |  |  | COA |  |  | 2021-11-11
| Supply and Delivery of Ofice Suuplies and Consumables for the Provision of Learning Resources on the Implementation of BE-LCP | [19 empty] | CID | NO | NP-53.9 - Small Value Procurement | 2021-09-11 | 11/11-11/17/2021 | 11/22/2021 | 11/22/2021 | 11/22/2021 |  | 11/23/2021 | 11/25/2021 | 11/25/2021 | 11/25/2021 | 11/29/2021 |  |  | GoP | 204140 |  |  | 204060 |  |  | COA |  |  | 2021-11-11
| Supply and Delivery of Common Use Suplies and Equipment for the Division Office Supplies | [19 empty] | OSDS | NO | NP-53.9 - Small Value Procurement | 11/22/2021 | 11/24-12/3/2021 | 2021-03-12 | 2021-03-12 | 2021-03-12 |  | 2021-03-12 | 2021-07-12 | 2021-09-12 | 2021-09-12 | 2021-10-12 |  |  | GoP | 253596 |  |  | 224000 |  |  | COA |  |  | 11/24/2021
| Lease of Training Venue including Accommodation, Food and Use of Facilities and Amenities for the conduct of School Base Feeding Program Implementation Assessment and Evaluation for SY 2021-2022 on March 23-25, 2022 | [19 empty] | SGOD | YES | NP-53.9 - Small Value Procurement | 2021-03-12 | 12/7-12/13/2021 | 12/14/2021 | 12/15/2021 | 12/15/2021 |  | 12/16/2021 | 12/20/2021 | 12/21/2021 | 12/21/2021 | 12/22/2021 |  |  | GoP | 248400 |  |  | 248400 |  |  | COA |  |  | 2021-07-12
| Supply and Delivery of Office Supplies and Consumables for the Provision of Learning Resources in the Implementation of the BE-LCP | [19 empty] | CID | NO | NP-53.9 - Small Value Procurement | 2021-09-12 | 12/11-12/16/2021 | 12/20/2021 | 12/20/2021 | 12/20/2021 |  | 12/21/2021 | 12/23/2021 | 12/24/2021 | 12/24/2021 | 12/27/2021 |  |  | GoP | 300015 |  |  | 298998 |  |  | COA |  |  | 2021-11-12
| Lease of Training Venue including Accommodation, Food and Use of Facilities and Amenities of participants during the conduct of Development and Quality Assurance of Project MAKE (Materials Appropriate for Kindergarten Education) | [19 empty] | CID | NO | Shopping | 2021-09-06 | 6/30-7/2/2021 |  |  |  |  | 2021-07-06 | 2021-07-08 | 2021-07-09 | 2021-07-12 | 2021-07-12 |  |  | GoP | 67500 |  |  | 67500 |  |  | COA
| Supply and Delivery of Meals and Snacks (7 lunch) (7 snacks AM&PM) for seven (7) days for the participants during the conduct of online training cum orientation on Early Language Liteeracy & Numeracy for Untrained EPSs, PSDSs, School Heads and K to 3 Untrained Teachers and Reading & ELLN Coordinators on August 9-13 & August 16-17, 2021 | [19 empty] | CID | NO | Shopping | 2021-09-06 | 6/15-6/18/2021 |  |  |  |  | 2021-06-23 | 2021-06-25 | 2021-06-28 | 2021-06-28 | 2021-06-29 |  |  | GoP | 70000 |  |  | 70000 |  |  | COA
| Supply and Delivery of Training Materials for the use of participants during the conduct of online training cum orientation on Early Language Literacy & Numeracy for Untrained EPSs, PSDSs, School Heads and K to 3 Untrained Teacers and Reading & ELLN Coordinators on August 9-13 and August 16-17, 2021 | [19 empty] | CID | NO | Shopping | 2021-09-06 | 6/15-6/18/2021 |  |  |  |  | 2021-06-23 | 2021-06-25 | 2021-06-28 | 2021-06-28 | 2021-06-29 |  |  | GoP | 80000 |  |  | 79566.8 |  |  | COA
| Supply and Delivery of Construction Materials including labor for the repare/installation of Tiles at Utility Office and Storage Room | [19 empty] | OSDS | NO | Shopping | 8/31/2021 | 9/6-9/13/2021 |  |  |  |  | 2021-09-14 | 2021-09-16 | 2021-09-17 | 2021-09-17 | 2021-09-20 |  |  | GoP | 60052.72 |  |  | 59907 |  |  | COA
| Lease of Training Venue including food, accommodation and use of facilities and amenities for the conduct of Division Finalization of the Storybooks intended for the Tagbanua and Batak Learners in the IPED Implementing Schools on September 27-29, 2021 | [19 empty] | CID | NO | Shopping | 9/13/2021 | 9/14-9/17/2021 |  |  |  |  | 2021-09-22 | 2021-09-24 | 2021-09-27 | 2021-09-27 | 2021-09-28 |  |  | GoP | 60000 |  |  | 60000 |  |  | COA
| Lease of Training venue including food, accommodation, and use of facilities and amenities for the conduct of Regional Online Training Workshop of Asatids Handling ALIVE classes on October 6-10, 2021 | [19 empty] | CID | NO | Shopping | 9/13/2021 | 9/17-9/24/2021 |  |  |  |  | 2021-09-24 | 2021-09-24 | 2021-09-29 | 2021-09-29 | 2021-09-30 |  |  | GoP | 90000 |  |  | 90000 |  |  | COA
| Supply and Delivery or Medical Suppplies and Health Equipment for COVID-19 Response and Intervention for Division Office Personnel and Schools | [19 empty] | SGOD | NO | Shopping | 9/20/2021 | 9/24-9/27/2021 |  |  |  |  | 2021-09-28 | 2021-09-30 | 2021-10-01 | 2021-10-01 | 2021-10-04 |  |  | GoP | 66710 |  |  | 61992 |  |  | COA
| Supply and Delivery of ICT Packages for DepEd Computerization Program (DCP) | [19 empty] | OSDS | NO | Shopping | 9/22/2021 | 9/30-10/7/2021 |  |  |  |  | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-14 |  |  | GoP | 100000 |  |  | 91637.7 |  |  | COA
| Supply and Delivery of Meals and Snacks of the Virtual Division Training on Gender and Development for Two (2) days on October 26-27, 2021 | [19 empty] | OSDS | NO | Shopping | 9/27/2021 | 10/13-10/19/2021 |  |  |  |  | 2021-10-21 | 2021-10-25 | 2021-10-26 | 2021-10-26 | 2021-10-27 |  |  | GoP | 120000 |  |  | 95995.2 |  |  | COA
| Supply and Delivery of Supplies and Other Consumables for the use in the conduct of Virtual Division Training on Gender and Development | [19 empty] | OSDS | NO | Shopping | 9/27/2021 | 10/13-10/19/2021 |  |  |  |  | 2021-10-21 | 2021-10-25 | 2021-10-26 | 2021-10-26 | 2021-10-27 |  |  | GoP | 108000 |  |  | 67855 |  |  | COA
| Supply and Delivery of food for the conduct of Development and Quality Assurance of Project Dream LRs for Quarter 2 Across Subject Areas | [19 empty] | CID | NO | Shopping | 10/19/2021 | 11/05-11/08/2021 |  |  |  |  | 2021-11-18 | 2021-11-22 | 2021-11-23 | 2021-11-23 | 2021-11-24 |  |  | GoP | 150000 |  |  | 149604 |  |  | COA
| Supply and Delivery of Supplies and materials for the printing of the self-learning materails as provision of the learning resources in the implementation of BE-LCP | [19 empty] | CID | NO | Shopping | 10/25/2021 | 11/01-11/04/2021 |  |  |  |  | 2021-11-11 | 2021-11-15 | 2021-11-16 | 2021-11-16 | 2021-11-17 |  |  | GoP | 86140 |  |  | 85264 |  |  | COA
| Supply and Delivery of Supplies and Materials for the printing of the Kindergarten Materrials as Provision of the Learning Resources in the Implementation of the BE-LCP | [19 empty] | CID | NO | Shopping | 10/25/2021 | 11/01-11/04/2021 |  |  |  |  | 2021-11-11 | 2021-11-15 | 2021-11-16 | 2021-11-16 | 2021-11-17 |  |  | GoP | 72275 |  |  | 71540 |  |  | COA
| Repair and Maintenance of Desktop & Laptop Computers in Records Section, Medical Section, CID Office and SDS Office | [19 empty] | OSDS | NO | Shopping | 2021-09-11 | 11/12-11/15/2021 |  |  |  |  | 2021-11-18 | 2021-11-22 | 2021-11-23 | 2021-11-23 | 2021-11-24 |  |  | GoP | 79000 |  |  | 78920 |  |  | COA
| Lease of Training Venue including Accommodation, Food, Use of Facilities and Amenities for Division Retooling of Untrained Teachers and School Heads Serving IPED Implementing Schools | [19 empty] | CID | NO | Shopping | 11/16/2021 | 11/18-11/22/2021 |  |  |  |  | 2021-11-23 | 2021-11-26 | 2021-11-29 | 2021-11-29 | 2021-12-01 |  |  | GoP | 60000 |  |  | 60000 |  |  | COA
| Supply and Delivery of Office Equipment for New IPED Implementing Schools for Alternative Learning Delivery | [19 empty] | CID | NO | Shopping | 11/16/2021 | 11/17-11/19/2021 |  |  |  |  | 2021-12-03 | 2021-12-07 | 2021-12-09 | 2021-12-09 | 2021-12-10 |  |  | GoP | 52500 |  |  | 52430 |  |  | COA
| Lease of Training Venue including Meals and Snacks for the Participants for One (1) day for the conduct of 2021 Division Brigada Eskwela Awarding Cum Partnership Appreciation Program | [19 empty] | SGOD | YES | Shopping | 11/16/2021 | 12/5-12/7/2021 |  |  |  |  | 2021-12-21 | 2021-12-23 | 2021-12-24 | 2021-12-24 | 2021-12-27 |  |  | GoP | 131000 |  |  | 130000 |  |  | COA
| Supply and Delivery of Construction Materials including Labor for the construction of comfort room and waiting shed | [19 empty] | OSDS | NO | Shopping | 9/31/2021 | 9/21-9/24/2021 |  |  |  |  | 2021-09-28 | 2021-09-30 | 2021-10-01 | 2021-10-01 | 2021-10-04 |  |  | GoP | 129440.35 |  |  | 129224.73 |  |  | COA
| Lease of Training Venue including Accommodation, Food and use of facilities and amenities for the conduct of 2021 Year-End Workshop on the Preparaton of Unified Reports and Consolidation of Budget and Financial Accountability Reports (BFARS) | [19 empty] | OSDS | NO | Shopping | 2021-03-12 | 12/5-12/7/2021 |  |  |  |  | 2021-12-10 | 2021-12-14 | 2021-12-16 | 2021-12-16 | 2021-12-17 |  |  | GoP | 64000 |  |  | 64000 |  |  | COA
| Lease of Training Venue including Accommodation, Food and use of facilities and Amenities for the conduct of PPC Basic Education Research Summit on November 11-12, 2021 | [19 empty] | SGOD | NO | Shopping | 10/19/2021 | 10/26-10/29/2021 |  |  |  |  | 2021-10-29 | 2021-11-03 | 2021-11-04 | 2021-11-04 | 2021-11-05 |  |  | GoP | 54000 |  |  | 54000 |  |  | COA
| Lease of Training Venue including meals and snacks for the conduct of meeting & orientation on the implementation of comprehensive sexuality education-adolescent reproductive health (CSE-ARH) for CSE-ARH focal persons and school heads on January 27-28,2022 (TWG) and February 9-11,2022 (focal persons and school heads) | [19 empty] | SGOD | YES | Shopping |  | 12/7-12/9/2021 |  |  |  |  | 2021-12-16 | 2021-12-20 | 2021-12-21 | 2021-12-21 | 2021-12-22 |  |  | GoP | 100000 |  |  | 99000 |  |  | COA
| Repair of Division Office Driveway | [19 empty] | OSDS | NO | Shopping | 11/22/2021 | 11/24-11/26/2021 |  |  |  |  | 2021-12-03 | 2021-12-07 | 2021-12-09 | 2021-12-09 | 2021-12-10 |  |  | GoP | 124550 |  |  | 124245 |  |  | COA
| Supply and Delivery of office supplies and consumables including office equipment for the use of Madrasah ALIVE Teachers | [19 empty] | CID | NO | Shopping | 2021-06-02 | [5 empty] | 2021-06-14 | 2021-06-17 | 2021-06-21 | 2021-06-23 | 2021-06-24 |  |  | GoP | 42128 |  |  | 42000 |  |  | COA
| Supply and Delivery of Training Materials for the conduct of Project TEAM (Training for Educational Advancement in Multigrade) | [19 empty] | CID | NO | Shopping | 2021-06-09 | [5 empty] | 2021-06-23 | 2021-06-25 | 2021-06-28 | 2021-06-28 | 2021-06-29 |  |  | GoP | 37150 |  |  | 37086 |  |  | COA
| Supply and Delivery of Meals and Snacks (2 lunch, 4 snacks - AM & PM) for two (2) days of participants during the conduct of Project TEAM (Training for Educational Advancement in Multigrade) | [19 empty] | CID | NO | Shopping | 2021-06-09 | [5 empty] | 2021-06-23 | 2021-06-25 | 2021-06-28 | 2021-06-28 | 2021-06-29 |  |  | GoP | 2850 |  |  | 2849 |  |  | COA
| Supply and Delivery of Meals (lunch) ad Snacks (AM & PM) of the participants for the conduct of four-day activity on Finalization of Special Education Learning Activity Sheets (SELAS) | [19 empty] | CID | NO | Shopping | 2021-07-05 | [5 empty] | 2021-07-16 | 2021-07-21 | 2021-07-22 | 2021-07-22 | 2021-07-23 |  |  | GoP | 30000 |  |  | 29994 |  |  | COA
| Supply and Delivery of Meals (lunch) and Snacks (AM&PM) of the participants for the conduct of Online Orientation of the Development and Quality Assurance of Project DREAM (Digitized Resources in Education for Applicalbe Modality) on Learning Resources Across Subject Areas | [19 empty] | CID | NO | Shopping | 2021-05-07 | [5 empty] | 2021-06-23 | 2021-06-25 | 2021-06-28 | 2021-06-28 | 2021-06-29 |  |  | GoP | 15000 |  |  | 14796 |  |  | COA
| Supply and Delivery of Training Materials for the conduct of Online Training for Elementary, JHS, and SHS Guidance Counselors and Designates | [19 empty] | CID | NO | Shopping | 2021-07-15 | [5 empty] | 2021-08-02 | 2021-08-04 | 2021-08-05 | 2021-08-05 | 2021-08-06 |  |  | GoP | 10000 |  |  | 9967 |  |  | COA
| Supply and Delivery of Meals (Lunch) and Snacks (AM & PM) of the participants to the conduct of three-day activity on Webinar on OK sa DepEd | [19 empty] | SGOD | NO | Shopping | 7/15/2021 | [5 empty] | 2021-08-02 | 2021-08-04 | 2021-08-05 | 2021-08-05 | 2021-08-06 |  |  | GoP | 30000 |  |  | 29700 |  |  | COA
| Supply and Delivery of Meals and Snacks of the participants for the conduct of Division Training on Core Competencies and Skills for First Level Non-Teaching Personnel | [19 empty] | SGOD | NO | Shopping | 7/15/2021 | [5 empty] | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 |  |  | GoP | 45000 |  |  | 44991 |  |  | COA
| Supply and Delivery of Training Materials for the use of participant for the conduct of Division Training on Core Competencies and Skills for First Level Non-Teaching Personnel | [19 empty] | SGOD | NO | Shopping | 7/15/2021 | [5 empty] | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 |  |  | GoP | 45310 |  |  | 45197 |  |  | COA
| Repair of Wooden Shelves/Cabinet and Tables in New Cash & Records Offices including Labor | [19 empty] | SGOD | NO | Shopping | 7/15/2021 | [5 empty] | 2021-08-02 | 2021-08-04 | 2021-08-05 | 2021-08-05 | 2021-08-06 |  |  | GoP | 49950 |  |  | 49826 |  |  | COA
| Supply and Delivery of Meals and Snacks of the Division Screening and Selection Committeee (DSSC) for the conduct of Division Screening and Selection of National Potential Learning Resource Evaluation (LREs) | [19 empty] | CID | NO | Shopping | 7/30/2021 | [5 empty] | 2021-08-16 | 2021-08-18 | 2021-08-19 | 2021-08-19 | 2021-08-20 |  |  | GoP | 27000 |  |  | 26994 |  |  | COA
| Supply and Delivery of Meals and snacks of Program Management Team for five (5) days during the conduct of Virtual 25th Founding Anniversary of the City DepEd on September 1-3 and 6-7, 2021 | [19 empty] | OSDS | NO | Shopping | 8/16/2021 | [5 empty] | 2021-08-24 | 2021-08-26 | 2021-08-27 | 2021-08-27 | 2021-08-31 |  |  | GoP | 49500 |  |  | 49500 |  |  | COA
| Supply and Delivery of Meals and Snacks for three (3) days for the conduct of Capacity-Building on conducting Research for Non-Teaching Personnel on September 8-10, 2021 | [19 empty] | SGOD | NO | Shopping | 8/16/2021 | [5 empty] | 2021-08-24 | 2021-08-27 | 2021-08-31 | 2021-08-31 | 2021-09-01 |  |  | GoP | 49500 |  |  | 49490 |  |  | COA
| Supply and Delivery of Meals and Snacks for three (3) days fr the conduct of Seminar-Workshop on Program Management Principles Concepts and Essential Skills on September 29-October 1, 2021 | [19 empty] | SGOD | NO | Shopping | 8/16/2021 | [5 empty] | 2021-08-24 | 2021-08-27 | 2021-08-31 | 2021-08-31 | 2021-09-01 |  |  | GoP | 45000 |  |  | 44991 |  |  | COA
| Supply and Delivery of Meals and Snacks of the PMT for 3 days during the condut of the 2021 World Teachers Day Celebration | [19 empty] | SGOD | NO | Shopping | 9/13/2021 | [5 empty] | 2021-09-23 | 2021-09-24 | 2021-09-27 | 2021-09-27 | 2021-09-28 |  |  | GoP | 37500 |  |  | 37492.5 |  |  | COA
| Supply and Delivery of Meals and Snacks for one (1) day for the conduct of Private Schools Conference on September 24, 2021 | [19 empty] | SGOD | NO | Shopping | 9/13/2021 | [5 empty] | 2021-09-23 | 2021-09-24 | 2021-09-27 | 2021-09-27 | 2021-09-28 |  |  | GoP | 20000 |  |  | 19900 |  |  | COA
| Supply and Delivery of Meals and Snacks for one (1) day for the conduct of Orientation of New DRRM and Physical Facilities Coordinators on RA 101201, DO No. 21 s. 2015, and EO 66 | [19 empty] | SGOD | NO | Shopping | 9/13/2021 | [5 empty] | 2021-09-23 | 2021-09-24 | 2021-09-27 | 2021-09-27 | 2021-09-28 |  |  | GoP | 15000 |  |  | 14997 |  |  | COA
| Supply and Deliverry of Meals and Snacks for Training Workshop of ALS Implementers on the Preparation of Life Skills Business Proposal on September 28-30,2021 | [19 empty] | CID | NO | Shopping | 9/13/2021 | [5 empty] | 2021-09-23 | 2021-09-24 | 2021-09-27 | 2021-09-27 | 2021-09-28 |  |  | GoP | 33750 |  |  | 37675 |  |  | COA
| Supply and Delivery of Training Materrials for the condduct of Training Workshop of ALS Implementeers on the Preparation of Life skills Business Proposal on September 28-30, 2021 | [19 empty] | CID | NO | Shopping | 9/13/2021 | [5 empty] | 2021-09-22 | 2021-09-24 | 2021-09-27 | 2021-09-27 | 2021-09-28 |  |  | GoP | 6250 |  |  | 6234 |  |  | COA
| Supply and Delivery of Supplies and Materials during the conduct of 2021 World Teachers Day | [19 empty] | SGOD | NO | Shopping | 9/13/2021 | [5 empty] | 2021-09-22 | 2021-09-24 | 2021-09-27 | 2021-09-27 | 2021-09-28 |  |  | GoP | 35000 |  |  | 34979 |  |  | COA
| Supply and Delivery of Meals and snacks for one (1) day for the conduct of Youth formation Development Tribute for Teachers on october 4, 2021 | [19 empty] | SGOD | NO | Shopping | 9/20/2021 | [5 empty] | 2021-09-28 | 2021-09-30 | 2021-10-01 | 2021-10-01 | 2021-10-04 |  |  | GoP | 10000 |  |  | 9998 |  |  | COA
| Supply and Delivery of Supplies and Materials during the conuct of Youth Formation Development Tribue for Teachers on October 4, 2021 | [19 empty] | SGOD | NO | Shopping | 9/20/2021 | [5 empty] | 2021-09-28 | 2021-09-30 | 2021-10-01 | 2021-10-01 | 2021-10-04 |  |  | GoP | 11000 |  |  | 10980 |  |  | COA
| Supply and Delivery of Supplies and Materials for the conduct of Webinar on Road Safety wareness for Supreme Student Government and Supreme Pupil Government Officers and Their Advisers on november 16, 2021 | [19 empty] | SGOD | NO | Shopping | 9/20/2021 | [5 empty] | 2021-10-11 | 2021-10-13 | 2021-10-14 | 2021-10-14 | 2021-10-15 |  |  | GoP | 2760 |  |  | 2758 |  |  | COA
| Supply and Delivery of Meas and Snacks for 2 days for the conduct of Annual Planning | [19 empty] | SGOD | NO | Shopping | 9/20/2021 | [5 empty] | 2021-09-28 | 2021-09-30 | 2021-10-01 | 2021-10-01 | 2021-10-04 |  |  | GoP | 30000 |  |  | 29994 |  |  | COA
| Lease of Venue, meals and snacks and printed t-shirt for the conduct of two days for the 2021 3rd Quarter Workshop on the Preparation of Unified Reports and Consolidation of Budget & Financial Reports (BFARS) | [19 empty] | OSDS | NO | Shopping | 9/20/2021 | [5 empty] | 2021-09-28 | 2021-09-30 | 2021-10-01 | 2021-10-01 | 2021-10-04 |  |  | GoP | 35000 |  |  | 34904 |  |  | COA
| Supply and Delivery of Meals and Snacks for the conductt of DEDP Revisit | [19 empty] | SGOD | NO | Shopping | 9/20/2021 | [5 empty] | 2021-09-28 | 2021-09-30 | 2021-10-01 | 2021-10-01 | 2021-10-04 |  |  | GoP | 35000 |  |  | 34965 |  |  | COA
| Supply and Delivery of Meals and Snacks during the conduct of Division Virtual Orientation on Barkada Kontra Droga (BKD) Program School Coordinators on November 19,2021 | [19 empty] | SGOD | NO | Shopping | 9/20/2021 | [5 empty] | 2021-10-11 | 2021-10-13 | 2021-10-14 | 2021-10-14 | 2021-10-15 |  |  | GoP | 15000 |  |  | 14997 |  |  | COA
| Supply and Delivery of Supplies and Materials for the use in the conduct of Personal Financial Management Training for Newly Hireed Personnel on October 26-28,2021 | [19 empty] | SGOD | NO | Shopping | 9/27/2021 | [5 empty] | 2021-10-11 | 2021-10-13 | 2021-10-14 | 2021-10-14 | 2021-10-15 |  |  | GoP | 5000 |  |  | 4998 |  |  | COA
| Supply and Delivery of Meals and Snacks for the conduct of Personal Financial Management Training for Newly Hired Personnel on October 26-28,2021 | [19 empty] | SGOD | NO | Shopping | 9/27/2021 | [5 empty] | 2021-10-11 | 2021-10-13 | 2021-10-14 | 2021-10-14 | 2021-10-15 |  |  | GoP | 45000 |  |  | 44991 |  |  | COA
| Supply and Delivery of Meal and Snacks for the Orientation Meeting of LIS Coordinators on october 20-23, 2021 | [19 empty] | SGOD | NO | Shopping | 9/27/2021 | [5 empty] | 2021-10-11 | 2021-10-13 | 2021-10-14 | 2021-10-14 | 2021-10-15 |  |  | GoP | 15750 |  |  | 15738.75 |  |  | COA
| Supply and Delivery of Meals and Snacks for the conduct of one (1) day celebration of the National Indigenous Peoples Month 2021 on October 28, 2021 | [19 empty] | CID | NO | Shopping | 2021-07-10 | [5 empty] | 2021-10-21 | 2021-10-25 | 2021-10-26 | 2021-10-26 | 2021-10-27 |  |  | GoP | 16000 |  |  | 15996 |  |  | COA
| Repainting of Roof at Division Office | [19 empty] | OSDS | NO | Shopping | 10/19/2021 | [5 empty] | 2021-11-11 | 2021-11-15 | 2021-11-16 | 2021-11-16 | 2021-11-17 |  |  | GoP | 16000 |  |  | 15996 |  |  | COA
| Supply and Delivery of Advocacy Polo Shirt (Sublimated Dri-Fit) with OK sa DepEd Logo for Health and Nutrition Section Personnel | [19 empty] | SGOD | NO | Shopping | 10/19/2021 | [5 empty] | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-29 | 2021-11-02 |  |  | GoP | 17520 |  |  | 17496 |  |  | COA
| Supply and Delivery of Supplies and Materials for the Capacity Building of Supply Offficeers, Property custodians, and School BAC Members on Asset Management and General Accounting Manual on November 3-5,2021 | [19 empty] | SGOD | NO | Shopping | 10/19/2021 | [5 empty] | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-29 | 2021-11-02 |  |  | GoP | 5900 |  |  | 5808 |  |  | COA
| Supply and Delivery of Supplies and Materials for the 2020 BERF Grantees of PPC | [19 empty] | SGOD | NO | Shopping | 10/19/2021 | [5 empty] | 2021-10-29 | 2021-11-03 | 2021-11-04 | 2021-11-04 | 2021-11-05 |  |  | GoP | 39000 |  |  | 38918 |  |  | COA
| Supply and Delivery of Meals and snacks or One (1) day durin the conduct of Research oral Defense in Preparation for PPC Research Summit | [19 empty] | SGOD | NO | Shopping | 10/19/2021 | [5 empty] | 2021-10-29 | 2021-11-03 | 2021-11-04 | 2021-11-04 | 2021-11-05 |  |  | GoP | 17500 |  |  | 17496.5 |  |  | COA
| Supply and Delivery of Meals and Snacks for the Production Team for Five (5) days for the Production of Division Research Manual and Journal | [19 empty] | SGOD | NO | Shopping | 10/25/2021 | [5 empty] | 2021-11-11 | 2021-11-15 | 2021-11-16 | 2021-11-16 | 2021-11-17 |  |  | GoP | 12500 |  |  | 12497.5 |  |  | COA
| Supply and Delivery of Supplies and Mtrials for the Printing of Research Manual and Journal | [19 empty] | SGOD | NO | Shopping | 10/25/2021 | [5 empty] | 2021-11-11 | 2021-11-15 | 2021-11-16 | 2021-11-16 | 2021-11-17 |  |  | GoP | 21150 |  |  | 21050 |  |  | COA
| Lease of Training Venue including food, accommdoation, and use of facilities and amenities for the conduct of checkking, editing, and formatting of the Division Research Manual | [19 empty] | SGOD | NO | Shopping | 10/25/2021 | [5 empty] | 2021-11-11 | 2021-11-15 | 2021-11-16 | 2021-11-16 | 2021-11-17 |  |  | GoP | 28800 |  |  | 28800 |  |  | COA
| Supply and Delivery of Battery for the Service Vehicle | [19 empty] | SGOD | NO | Shopping | 10/28/2021 | [5 empty] | 2021-11-11 | 2021-11-15 | 2021-11-16 | 2021-11-16 | 2021-11-17 |  |  | GoP | 6500 |  |  | 6500 |  |  | COA
| Repair and Maintenance of Comcolor Machine at LRMDS | [19 empty] | CID | NO | Shopping | 10/28/2021 | [5 empty] | 2021-11-11 | 2021-11-15 | 2021-11-16 | 2021-11-16 | 2021-11-17 |  |  | GoP | 24000 |  |  | 23960 |  |  | COA
| Repair, Installation, and Maintennce o One (1) Unit Aircondition at New Legal Office and Cleaning of Four (4) Unit Airconditioning at CID Office | [19 empty] | OSDS | NO | Shopping | 2021-09-11 | [5 empty] | 2021-11-18 | 2021-11-23 | 2021-11-24 | 2021-11-24 | 2021-11-25 |  |  | GoP | 26708 |  |  | 26697 |  |  | COA
| Supply and Delivery of Supplies and Materials for the conduct of 5th Regional ALS Tagis Galing | [19 empty] | CID | NO | Shopping | 2021-09-11 | [5 empty] | 2021-11-17 | 2021-11-19 | 2021-11-22 | 2021-11-22 | 2021-11-23 |  |  | GoP | 30150 |  |  | 30043 |  |  | COA
| Supply and Delivery of Supplies and Materials for the use in the conduct of 2021 Division Brigada Eskwela Awarding on Partnership | [19 empty] | SGOD | NO | Shopping | 2021-09-11 | [5 empty] | 2021-11-10 | 2021-11-14 | 2021-11-15 | 2021-11-15 | 2021-11-16 |  |  | GoP | 35060 |  |  | 34650 |  |  | COA
| Repair, Installation of Billboard Frames and Repainting of Fences & SDS Office including Labor | [19 empty] | OSDS | NO | Shopping | 2021-06-11 | [5 empty] | 2021-11-23 | 2021-11-26 | 2021-11-29 | 2021-11-29 | 2021-12-01 |  |  | GoP | 38400 |  |  | 38320 |  |  | COA
| Lease of Training Venue including Accommodation, Food, Use of Facilities and Amenities for IPED Year-End Program Implementation Review and Target Setting for the Succeeding Year | [19 empty] | CID | NO | Shopping | 2021-06-11 | [5 empty] | 2021-11-23 | 2021-11-26 | 2021-11-29 | 2021-11-29 | 2021-12-01 |  |  | GoP | 31500 |  |  | 31500 |  |  | COA
| Supply, Delivery and Printing of Collared T-shirt with DepEd Logo | [19 empty] | SGOD | NO | Shopping | 2021-03-12 | [5 empty] | 2021-12-10 | 2021-12-14 | 2021-12-16 | 2021-12-16 | 2021-12-17 |  |  | GoP | 11392 |  |  | 11345 |  |  | COA
| Supply, Delivery and Installation of New Meter Reading of Division Office as Recommended by PALECO | [19 empty] | OSDS | NO | Shopping | 2021-03-12 | [5 empty] | 2021-12-21 | 2021-12-23 | 2021-12-24 | 2021-12-24 | 2021-12-27 |  |  | GoP | 40000 |  |  | 40000 |  |  | COA
[38 empty] | 0 |  |  | 0
Total Alloted Budget of Procurement Activities | [37 empty] | 77293993.96
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 78366813.47
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | -1072819.51
0N-GOING PROCUREMENT ACTIVITIES
| Supply and Delivery of Drugs and Medicines with Dental Supplies and Equipment for the Additional Maintenance and other Operating Expenses (MOOE) for the Provision of New Normal Set-Up for Minimum Heal | [19 empty] | SGOD | NO | Competitive Bidding |  | 3/28-4/18/2022 | 2021-04-04 | 4/18/2021 | 4/18/2021 | [8 empty] | GoP | 2523585
0
0
0
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 2523585
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | ANNA MYLENE F. NATIVIDAD | [9 empty] | MARITES P. PEREZ, EdD, CESE | [11 empty] | LOIDA PALAY ADORNADO PhD, CESO VI
[21 empty] | BAC Secretariat | [9 empty] | BAC Chairperson | [11 empty] | Head of the Procuring Entity

## Sheet1
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement