## Sheet1
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | DEPARTMENT OF EDUCATION - SDO PUERTO PRINCESA CTY Procurement Monitoring Report as of JANUARY 1 TO JUNE 30, 2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| Supply and Delivery of Drugs and Medicine with Dental Supplies and Equipment for the Additional Maintenance and other Operating Expenses (MOOE) for the Provision of New Normal Set Up for Minimum Health Standards for COVID-19 Related Office ad Public Schools | [19 empty] | SGOD | NO | Competitive Bidding | 2022-03-03 | 3/28/2022 | 2022-04-04 | 4/18/2022 | 4/18/2022 | 4/19/2022 | 4/21-22/2022 | 4/26/2022 | 4/27/2022 | 4/29/2022 | 2022-02-05 | 15 days |  | GoP | 2523670 |  | 2523670 | 2523195 |  |  | COA, PPC Chamber of Commerce | 2022-01-04 | 2022-01-04 | 2022-01-04 | 4/18/2022 | 4/18/2022 | 15 dys
| Supply and Delivery of Common Use Supplies and Consumables for the Printing of Quarter 4 K to 12 Materials for the Provision of Learning Resources in the Implementation of the Basic Education – Learning Continuity Plan (BE-LCP) | [19 empty] | CID | NO | Competitive Bidding | 2022-04-04 | 2022-07-04 | 4/13/2022 | 4/26/2022 | 4/26/2022 | 4/28/2022 | 4/29/2022 | 2022-05-05 | 2022-06-05 | 2022-11-05 | 2022-12-05 |  |  | GoP | 2076595 |  | 2076595 | 1408275 |  |  | COA, PPC Chamber of Commerce | 2022-11-04 | 2022-11-04 | 4/22/2022 | 4/25/2022 | 4/26/2022 | 15 days
| Supply and Delivery of Common Use Supplies, Equipment and Consumables for the Printing of K to 12 Materials for the Provision of Learning Resources of SY 2021-2022 under the Basic Education Learning Continuity Plan (BE-LCP) | [19 empty] | CID | NO | Competitive Bidding | 2022-04-04 | 4/7/2022 | 4/13/2022 | 4/26/2022 | 4/26/2023 | 4/28/2022 | 4/29/2022 | 5/5/2022 | 5/6/2022 | 2022-11-05 | 2022-12-05 | 15 days |  | GoP | 4279200 |  | 2076595 | 2626400 |  |  | COA, PPC Chamber of Commerce | 2022-06-04 | 2022-06-04 | 2022-06-05 | 4/28/2022 | 4/29/2022
| Supply and Delivery to School Drop Off Points of Nutritious Food Products and Commercial Milk Component for the Implementation of the School Based Feeding Program (SBFP) for SY 2021-2022 | [19 empty] | SGOD | NO | Competitive Bidding | 2022-04-04 | 4/7/2022 | 4/13/2022 | 4/26/2022 | 4/26/2023 | 4/28/2022 | 4/29/2022 | 5/5/2022 | 5/6/2022 | 2022-11-05 | 2022-12-05 | 15 days |  | GoP | 9705298 |  | 9705298 | 9047407 |  |  | COA, PPC Chamber of Commerce | 2022-06-04 | 2022-06-04 | 2022-06-05 | 4/28/2022 | 4/29/2022
| Lease of Venue for the conduct of Capacity Building Program for Teaching and Non- Teaching Personnel on The Use of Open Educational Resources (Proficiency and Transformational Stage) Educational Technology and ICT Tools for Batch 1 and Batch 2 | [19 empty] | OSDS | NO | Competitive Bidding | 4/26/2022 | 4/27/2022 | 5/13/2022 | 5/25/2022 | 5/25/2022 | 5/25/2022 | 5/25/2022 | 5/25/2022 | 5/26/2022 | 5/26/2022 | 5/27/2022 | 6 days |  | GoP | 2028000 |  | 2028000 | 2028000 |  |  | COA, PPC Chamber of Commerce | 5/10//2022 | 2022-10-05 | 2022-10-05 | 2022-10-05 | 2022-10-05
| Lease of Venue Full Board, Accommodation including Meals and use of Facilities and Amenities for the conduct of PYC 2022 on June 14-17,2022 | [19 empty] | OSDS | NO | Competitive Bidding | 5/18/2022 | 5/19/2022 | 5/27/2022 | 2022-08-06 | 2022-08-06 | 2022-06-06 | 2022-08-06 | 2022-09-06 | 2022-10-06 | 2022-10-06 | 6/13/2022 | 4 days |  | GoP | 17492000 |  | 17492000 | 17490500 |  |  | COA, PPC Chamber of Commerce | 5/24/2022 | 5/24/2022 | 5/24/2022 | 5/24/2022 | 5/24/2022
| Services of Trucking for the Delivery of Procured Self Learning Materials for Public Elementary and Secondary Schools | [19 empty] | CID | NO | NP-53.9 - Small Value Procurement | 1/19/2022 | 1/21/2022 |  | 2022-02-02 | 2022-02-02 | 2022-04-02 |  | 2022-08-02 | 2022-09-02 | 2022-09-02 | 2022-10-02 | 15 days |  | GoP | 402585 |  | 402585 | 348000 |  |  | COA, PPC Chamber of Commerce | 1/28/2022 | 1/28/2022 | 1/28/2022 | 2022-03-02 | 2022-03-02
| Supply and Delivery of Meals (Lunch) for Ten (10) days for the conduct of Development and Quality Assurance of Project Dream (Digitized Resources in Education for Applicable Modality) LRs for Quarter 3 and 4 Across Subject Areas, ALS and SPED | [19 empty] | CID | NO | NP-53.9 - Small Value Procurement | 1/19/2022 | 1/21/2022 |  | 2022-02-02 | 2022-02-02 | 2022-04-02 |  | 2022-08-02 | 2022-09-02 | 2022-09-02 | 2022-10-02 | 10 days |  | GoP | 400000 | 400000 |  | 290000 |  |  | COA, PPC Chamber of Commerce | 1/28/2022 | 1/28/2022 | 1/28/2022 | 2022-03-02 | 2022-03-02
| Supply and Delivery of Learners and Teachers Kit and Hygiene Items as ` Response intervention to the Affected Learners, Teachers, and Non-Teaching Personnel by Typhoon Odette | [19 empty] | SGOD | NO | NP-53.9 - Small Value Procurement | 2022-04-04 | 2022-07-04 |  | 4/13/2022 | 4/13/2022 |  | 4/20/2022 | 4/22/20222 | 4/25/2022 | 4/25/2022 | 4/26/2022 | 7 days |  | GoP | 203176 |  | 203176 | 168525 |  |  | COA, PPC Chamber of Commerce |  | 2022-08-04 | 2022-08-04 |  | 4/18/2022 | 7 days
| Procurement of Medical Devices Including Services of Trained Medical Practitioner/Technician to perform the Antigen Testing of the Participants for the conduct of Capacity Building Program for Teaching and Non-Teaching Personnel on the Use of Open Educational Resource Proficiency and Transformational Stage Educational Technology and ICT Tools for Batch 1 and 2 | [19 empty] | OSDS | NO | NP-53.9 - Small Value Procurement | 4/25/20222 | 2022-05-05 |  | 5/13/2022 | 5/13/2022 |  | 5/16/2022 | 5/18/2022 | 5/19/2022 | 5/19/2022 | 5/20/2022 | 3 days |  | GoP | 236600 |  | 236600 | 236600 |  |  | COA | 4/20/2022 | 4/20/2022 | 4/20/2022 |  | 2022-12-05 | 3 days
| Supply and Delivery of Information Technology Devices for the Prototype Educational Technology and ICT Tools and Equipment to the 2 Pilot Schools of SDO PPC and Capacity Building Program for Teaching and Non-Teaching Personnel on the Use of Open Educational Resource Proficiency and Transformational Stage Educational Technology and ICT Tools for Batch 1 and Batch 2 | [19 empty] | OSDS | NO | NP-53.9 - Small Value Procurement | 5/25/2022 | 4/27/2022 |  | 5/13/2022 | 5/13/2022 |  | 5/16/2022 | 5/18/2022 | 5/19/2022 | 5/19/2022 | 5/20/2022 |  |  | GoP | 767410 |  | 767410 | 703296 |  |  | COA, PPC Chamber of Commerce |  | 2022-10-05 | 2022-10-05 |  | 2022-12-05 | 5 days
| Supply and Delivery of Meals and Snacks for the Working Committee Stakeholders, Teacher Facilitators, Guest and Resource Persons for the conduct of PYC 2022 | [19 empty] | OSDS | NO | NP-53.9 - Small Value Procurement | 5/25/2022 | 5/30/2022 |  | 2022-06-06 | 2022-06-06 |  | 2022-07-06 | 2022-09-06 | 2022-10-06 | 2022-10-06 | 6/13/2022 |  |  | GoP | 845000 |  | 845000 | 709800 |  |  | COA, PPC Chamber of Commerce |  | 2022-01-06 | 6/1/2022 |  | 2022-02-06 | 7 days
| Rental of Vehicles and Services for the conduct of PYC 2022 | [19 empty] | OSDS | NO | NP-53.9 - Small Value Procurement | 5/25/2022 | 5/30/2022 |  | 2022-06-06 | 2022-06-06 |  | 2022-07-06 | 2022-09-06 | 2022-10-06 | 2022-10-06 | 6/13/2022 |  |  | GoP | 276000 |  | 276000 | 269100 |  |  | COA, PPC Chamber of Commerce |  | 2022-01-06 | 6/1/2022 |  | 2022-02-06 | 10 days
| Lease of Training Venue including Food (Breakfast, Lunch and Dinner) & snacks PM only) , use of training facilities and amenities during the conduct of Disaster Risk Reduction Management (DRRM) Executive Conference cum Planning of DepEd DRRMCAP Officers and Board Members | [19 empty] | SGOD | NO | NP-53.9 - Small Value Procurement | 5/25/2022 | 5/30/2022 |  | 2022-06-06 | 2022-06-06 |  | 2022-07-06 | 2022-09-06 | 2022-10-06 | 2022-10-06 | 6/13/2022 |  |  | GoP | 370000 |  | 370000 | 370000 |  |  | COA, PPC Chamber of Commerce |  | 2022-01-06 | 6/1/2022 |  | 2022-02-06 | 10 days
| Supply and Delivery of Supplies Consumables and Materials to be used for the conduct of the PYC 2022 | [19 empty] | OSDS | NO | NP-53.9 - Small Value Procurement | 5/27/200 | 5/30/2022 |  | 2022-06-06 | 2022-06-06 |  | 2022-07-06 | 2022-09-06 | 2022-10-06 | 2022-10-06 | 6/13/2022 |  |  | GoP | 449595.72 |  | 449595.72 | 438144.5 |  |  | COA, PPC Chamber of Commerce |  | 2022-01-06 | 6/1/2022 |  | 2022-02-06 | 5 days
| Supply and Delivery fo Meals and Snacks for the SDO Working Committee for the PYC 2022 | [19 empty] | OSDS | NO | NP-53.9 - Small Value Procurement | 5/30/2022 | 2022-05-06 |  | 2022-06-06 | 2022-06-06 |  | 2022-10-06 | 2022-10-06 | 6/13/2022 | 6/13/2022 | 6/13/2022 |  |  | GoP | 737450 |  | 737450 | 736494.5 |  |  | COA, PPC Chamber of Commerce |  | 2022-01-06 | 2022-01-06 |  | 2022-08-06 | 7 days
| Supply,Delivery and Printing of Polo Shirt for the Participants of Reskilling of Digital Skills for Division Personnel | [19 empty] | SGOD | NO | Shopping | 2022-10-01 | 2022-11-01 |  | 1/17/2022 | 1/17/2022 |  | 1/20/2022 | 1/24/2022 | 1/25/2022 | 1/25/2022 | 1/26/2022 |  |  | GoP | 68400 |  | SARO OSEC – 4B-21-3294 dated 8/12/21 Php 1,000.000/00 | 68388.6 |  |  | COA |  | 2022-12-01 | 2022-12-01 |  | 1/18/2022 | 7 days
| Repair and Maintenance of Office Building 3rd Floor Hallway | [19 empty] | OSDS | NO | Shopping | 2022-11-02 | 2/16/2022 |  | 2/23/2022 | 2/23/2022 |  | 2/28/2022 | 2/28/2022 | 2022-01-03 | 2022-01-03 | 2022-02-03 |  |  | GoP | 124614.55 | 124614.55 |  | 90780 |  |  | COA |  | 2/18/2022 | 2/18/2022 |  | 2/23/2022 | 15 days
| Lease of Training Venue including Meal (Lunch) and Snacks (AM and PM) for the conduct of Division Orientation – Workshop on Learning Resource Management under Project SKIM (Safe-Keeping of instructional Materials) for School LR Coordinators/Librarians and Property Custodians | [19 empty] | CID | NO | Shopping | 2/18/2022 | 2/23/2022 |  | 2022-03-03 | 2022-03-03 |  | 2022-07-03 | 2022-09-03 | 2022-10-03 | 2022-10-03 | 2022-11-03 |  |  | GoP | 50000 | 50000 |  | 47553 |  |  | COA |  | 2/28/2022 | 2/28/2022 |  | 2022-03-03 | 1 day
| Lease of Training Venue including Meal (Lunch) and Snacks (AM and PM) for the conduct of Division Orientation – Workshop on Quality Assurance of Learning Resources for selected Learning Resource Evaluators (LREs) | [19 empty] | CID | NO | Shopping | 2/18/2022 | 2/23/2022 |  | 2022-03-03 | 2022-03-03 |  | 2022-07-03 | 2022-09-03 | 2022-10-03 | 2022-10-03 | 2022-11-03 |  |  | GoP | 100000 |  |  | 89600 |  |  | COA |  | 2/28/2022 | 2/28/2022 |  | 2022-03-03 | 2 days
| Prorcurement of Virtual Meeting for the use of Division Office under the Project Division ADVANCE (Augmented Virtual Access for the New Normal Conference Engagements) for One (1) Year Subscription | [19 empty] | CID | NO | Shopping | 2022-03-03 | 2/23/2022 |  | 2022-11-03 | 2022-11-03 |  | 2022-07-03 | 2022-09-03 | 2022-10-03 | 2022-10-03 | 2022-11-03 |  |  | GoP | 60000 |  |  | 59980 |  |  | COA |  | 2/28/2022 | 2/28/2022 |  | 2022-03-03
| Lease of Training Venue including Meals (Lunch) and Snacks (AM and PM) for One (1) day for the conduct of Division Seminar-Workshop on Project Symbol (Strategies on Yielding Mentors I Building Outstanding Learners | [19 empty] | CID | NO | Shopping | 2022-04-04 | 2022-07-04 |  | 2022-11-04 | 2022-11-04 |  | 2022-12-04 | 4/19/2022 | 4/20/2022 | 40/20/2022 | 4/21/2022 |  |  | GoP | 50000 | 50000 |  | 49500 |  |  | COA |  | 2022-06-04 | 2022-06-04 |  | 2022-08-04 | 1 day
| Supply and Delivery of Common Use Supplies of Division of Puerto Princesa City for 1st Quarter of CY 2022 | [19 empty] | OSDS | NO | Shopping | 2022-04-04 | 2022-07-04 |  | 2022-11-04 | 2022-11-04 |  | 4/13/2022 | 4/19/2022 | 4/20/2022 | 4/20/2022 | 4/21/2022 |  |  | GoP | 155642 | 155642 |  | 128114 |  |  | COA |  | 2022-06-04 | 2022-06-04 |  | 2022-11-04 | 7 days
| Procurement of Trucking Services including Hauling for the door-to-door delivery of the Regional Office Procured Quarter 3 and 4 Self –Learning Modules to all Public Elementary and Secondary Schools in the SDO of Puerto Princesa City | [19 empty] | CID | NO | Shopping | 2022-04-04 | 04/13/2022 |  | 04/18/2022 | 04/18/2022 |  | 4/19/2022 | 4/22/2022 | 4/25/2022 | 4/25/2022 | 4/26/2022 |  |  | GoP | 170875 |  | 170875 | 170000 |  |  | COA |  | 4/13/2022 | 4/13/2022 |  | 4/13/2022 | 15 days
| Supply and Delivery of Medicines and Medical Supplies to be used during the conduct of PYC 2022 | [19 empty] | OSDS | NO | Shopping | 5/25/2022 | 5/27/2022 |  | 5/30/2022 | 5/30/2022 |  | 5/31/2022 | 2022-02-06 | 2022-03-06 | 2022-03-06 | 2022-06-06 |  |  | GoP | 100882.5 |  | 100882.5 | 99839 |  |  | COA |  | 5/25/2022 | 5/25/2022 |  | 5/27/2022 | 3 days
| Lease of Training Venue including Meals (Lunch) and Snacks (AM and PM), use of Facilities and Amenities for Three (3) days for the conduct of Division Writeshop for the Development of Professional Development Programs for Teachers and | [19 empty] | SGOD | NO | Shopping | 5/25/2022 | 5/27/2022 |  | 5/30/2022 | 5/30/2022 |  | 5/31/2022 | 2022-02-06 | 2022-03-06 | 2022-03-06 | 2022-06-06 |  |  | GoP | 90000 |  | 90000 | 85500 |  |  | COA |  | 5/25/2022 | 5/25/2022 |  | 5/27/2022 | 3 days
| Rental Services of Light, Sounds and Equipment for the conduct of PYC 2022 | [19 empty] | OSDS | NO | Shopping | 5/27/2022 | 5/30/2022 |  | 2022-06-06 | 2022-06-06 |  | 2022-07-06 | 2022-09-06 | 2022-10-06 | 2022-10-06 | 6/13/2022 |  |  | GoP | 120000 |  | 120000 | 118000 |  |  | COA |  | 2022-01-06 | 2022-01-06 |  | 2022-03-06 | 3 days
| Rental of LED Wall Display Pe Type for the conduct of PYC 2022 | [19 empty] | OSDS | NO | Shopping | 5/27/2022 | 5/30/2022 |  | 2022-06-06 | 2022-06-06 |  | 2022-07-06 | 2022-09-06 | 2022-10-06 | 2022-10-06 | 6/13/2022 |  |  | GoP | 132000 |  | 132000 | 131500 |  |  | COA |  | 2022-01-06 | 2022-01-06 |  | 2022-03-06 | 3 days
| Rental of Video and Photo Equipment with accompanying Equipment Handlers for the PYC 2022 | [19 empty] | OSDS | NO | Shopping | 5/27/2022 | 5/30/2022 |  | 2022-06-06 | 2022-06-06 |  | 2022-07-06 | 2022-09-06 | 2022-10-06 | 2022-10-06 | 6/13/2022 |  |  | GoP | 160000 |  | 160000 | 158995 |  |  | COA |  | 2022-01-06 | 2022-01-06 |  | 2022-03-06 | 3 days
| Services of Surveyor (Geodetic Engineer) | [19 empty] | OSDS | NO | Shopping | 2022-08-06 | 2022-09-06 |  | 6/24/2022 | 6/24/2022 | [8 empty] | GoP | 90000 | [5 empty] | COA | [6 empty] | Failure due to non receipt of RFQs
| Supply and Delivery of Supplies and Materials for the ALS-PSF Fund | [19 empty] | CID | NO | Shopping | 2022-10-06 | 6/13/2022 |  | 6/20/2022 | 6/20/2022 |  | 6/21/2022 | 6/23/2022 | 6/24/2022 | 6/24/2022 | 6/27/200 |  |  | GoP | 124558 |  | 124558 | 124225 |  |  | COA |  | 6/16/2022 | 6/16/2022 |  | 6/17/2022 | 5 days
| Supply and Delivery of Meal and Snacks of participants for One (1) day on the conduct of Reskilling of Digital Skilles for Division Office Personnel | [19 empty] | CID | NO | Shopping | 2022-10-01 |  |  | 1/19/2022 | 1/19/2022 |  | 1/20/2022 | 1/24/2022 | 1/25/2022 | 1/25/2022 | 1/26/2022 |  |  | GoP | 15000 |  | 15000 | 14997 |  |  | COA |  | 1/14/2022 | 1/14/2022 |  | 1/17/2022 | 1 day
| Supply and Delivery of Supplies to be used in the conduct of Psychological First Aid and Mental Health Psychosocial Support sessions for Learners Teaching and Non-Teaching personel victims of thyphoon Odette | [19 empty] | SGOD | NO | Shopping | 2022-02-02 |  |  | 2022-11-02 | 2022-11-02 |  | 2/14/2022 | 2/16/2022 | 2/17/2022 | 2/17/2022 | 2/18/2022 |  |  | GoP | 48364 |  | 48364 | 47887.5 |  |  | COA |  | 2022-09-02 | 2022-09-02 |  | 2022-10-02 | 3 days
| Supply and Delivery of Meals and Snacks for Facilitators and Participants durig the conduct of Psychological First Aid and Mental Health Psychosocial sessions for Thyphoon Odette | [19 empty] | SGOD | NO | Shopping | 2022-02-02 |  |  | 2022-11-02 | 2022-11-02 |  | 2/14/2022 | 2/16/2022 | 2/17/2022 | 2/17/2022 | 2/18/2022 |  |  | GoP | 48460 |  | 48460 | 48360 |  |  | COA |  | 2022-09-02 | 2022-09-02 |  | 2022-10-02 | 3 days
| Supply and Delivery of Furniture and Fixtures (Steel Hanging Cabinet with sliding door) | [19 empty] | OSDS | NO | Shopping | 2022-02-02 |  |  | 2022-11-02 | 2022-11-02 |  | 2/14/2022 | 2/16/2022 | 2/17/2022 | 2/17/2022 | 2/18/2022 |  |  | GoP | 38000 | 38000 |  | 37990 |  |  | COA |  | 2022-09-02 | 2022-09-02 |  | 2022-10-02 | 5 days
| Supply and Delivery of ID with ID Lace and Casing ) | [19 empty] | OSDS | NO | Shopping | 2022-02-02 |  |  | 2022-11-02 | 2022-11-02 |  | 2/14/2022 | 2/16/2022 | 2/17/2022 | 2/17/2022 | 2/18/2022 |  |  | GoP | 43840 | 43840 |  | 43840 |  |  | COA |  | 2022-09-02 | 2022-09-02 |  | 2022-10-02 | 5 days
| Suppy,Delivery and Installation of 5 Acrylic Signages, Table Name Plate, Org.Chart/Map,Cicha, Cut –Out Sticker on Acrylic | [19 empty] | OSDS | YES | Shopping | 2022-02-02 |  |  | 2022-11-02 | 2022-11-02 |  | 2/14/2022 | 2/16/2022 | 2/17/2022 | 2/17/2022 | 2/18/2022 |  |  | GoP | 27534 | 27534 |  | 27519 |  |  | COA |  | 2022-09-02 | 2022-09-02 |  | 2022-10-02 | 5 days
| Supply,Delivery and Reproduction of Assorted Information Education and Communication (IEC) Materials for the Elementary and Secondary Schools of SDO PPC | [19 empty] | SGOD | NO | Shopping | 12/15/2022 |  |  | 2/18/2022 | 2/18/2022 |  | 2/21/2022 | 2/23/2022 | 2/24/2022 | 2/24/2022 | 2/28/2022 |  |  | GoP | 44940 |  | 44940 | 44940 |  |  | COA |  | 2/15/2022 | 2/15/2022 |  | 2/17/2022 | 30 days
| Supply and Delivery of Meal (Lunch) and Snacks (AM/PM) for One (1) day for the conduct of Division Virtual Orientation on DepEd Order No.44 s. 2021 cum launching of SPED Project FAC (Find a Child) | [19 empty] | CID | NO | Shopping | 2022-11-02 |  |  | 2/18/2022 | 2/18/2022 |  | 2/21/2022 | 2/23/2022 | 2/24/2022 | 2/24/2022 | 2/28/2022 |  |  | GoP | 4000 | 4000 |  | 4000 |  |  | COA |  | 2/15/2022 | 2/15/2022 |  | 2/17/2022 | 1 day
| Supply and Delivery of Meal (Lunch) and Snacks (AM/PM for the conduct of Training Orientation of Senior High School Coordinators, School Heads and Selected Teachers on Project SHSATS | [19 empty] | CID | NO | Shopping | 2022-11-02 |  |  | 2/18/2022 | 2/18/2022 |  | 2/21/2022 | 2/23/2022 | 2/24/2022 | 2/24/2022 | 2/28/2022 |  |  | GoP | 2000 | 2000 |  | 1500 |  |  | COA |  | 2/15/2022 | 2/15/2022 |  | 2/17/2022 | 1 day
| Supply and Delivery of Training Materials for the conduct of Training Orientation of Senior High School Coordinators, School Heads and Selected Teachers on Project SHSATS | [19 empty] | CID | NO | Shopping | 2022-11-02 |  |  | 2/18/2022 | 2/18/2022 |  | 2/21/2022 | 2/23/2022 | 2/24/2022 | 2/24/2022 | 2/28/2022 |  |  | GoP | 12960 | 12960 |  | 12560 |  |  | COA |  | 2/15/2022 | 2/15/2022 |  | 2/17/2022 | 5 days
| Repair, Maintenance of Office Building (Aircondition Units of Division Office) | [19 empty] | OSDS | NO | Shopping | 2022-11-02 |  |  | 2/18/2022 | 2/18/2022 |  | 2/21/2022 | 2/23/2022 | 2/24/2022 | 2/24/2022 | 2/28/2022 |  |  | GoP | 15600 | 15600 |  | 15050 |  |  | COA |  | 2/15/2022 | 2/15/2022 |  | 2/17/2022 | 7 days
| Supply and Delivery of Meal (Lunch) and Snacks (AM and PM) for the conduct of Division Virtual Seminar on Homeroom Guidance Program for School Heads, Guidance Counselors | [19 empty] | CID | NO | Shopping | 2/18/2022 |  |  | 2022-03-03 | 2022-03-03 |  | 2022-07-03 | 2022-09-03 | 2022-10-03 | 2022-10-03 | 2022-11-03 |  |  | GoP | 35000 | 35000 |  | 21000 |  |  | COA |  | 2/28/2022 | 2/28/2022 |  | 2022-03-03 | 3 days
| Supply and Delivery of Meal (Lunch) and Snacks (AM and PM) for the conduct of Division Virtual Seminar on Project E-Filled (Enabling Filipino Language Learning for Educators) on March 28, 2022 | [19 empty] | CID | NO | Shopping | 2/18/2022 |  |  | 2022-03-03 | 2022-03-03 |  | 2022-07-03 | 2022-09-03 | 2022-10-03 | 2022-10-03 | 2022-11-03 |  |  | GoP | 13000 | 13000 |  | 7800 |  |  | COA |  | 2/28/2022 | 2/28/2022 |  | 2022-03-03 | 1 day
| Supply and Delivery of Meals (Lunch) and Snacks (AM and PM) for the conduct of Division Virtual Reorientation on DepEd No. 35 s. 2016 Implementation of Learning Cell on March 18, 2022 | [19 empty] | SGOD | NO | Shopping | 2/23/2022 |  |  | 2022-07-03 | 2022-07-03 |  | 2022-08-03 | 2022-11-03 | 2022-11-03 | 3/14/2022 | 3/14/2022 |  |  | GoP | 30000 | 30000 |  | 19900 |  |  | COA |  | 2022-02-03 | 2022-02-03 |  | 2022-03-03 | 1 day
| Lease of Training Venue including Meals (Lunch) and Snacks (AM and PM) for the conduct of One (1) day Interfacing Activity on March 17, 2022 | [19 empty] | OSDS | NO | Shopping | 2/23/2022 |  |  | 2022-07-03 | 2022-07-03 |  | 2022-08-03 | 2022-11-03 | 2022-11-03 | 3/14/2022 | 3/14/2022 |  |  | GoP | 49800 | 49800 |  | 44820 |  |  | COA |  | 2022-02-03 | 2022-02-03 |  | 2022-03-03 | 1 day
| Lease of Training Venue including Meals and Snacks for the conduct of One (1) day First Quarter Division Monitoring and Evaluation Plan Adjustment (DMEPA) | [19 empty] | SGOD | NO | Shopping | 2022-03-03 |  |  | 2022-11-03 | 2022-11-03 |  | 3/14/2022 | 3/16/2022 | 3/17/2022 | 3/17/2022 | 3/18/2022 |  |  | GoP | 20000 | 20000 |  | 18000 |  |  | COA |  | 2022-08-03 | 2022-08-03 |  | 2022-10-03 | 1 day
| Supply and Delivery of Tubeless Tires 195R 15C for City DepEd Service Vehicle Toyota Commuter – New (CS-P5E271) | [19 empty] | OSDS | NO | Shopping | 2022-03-03 |  |  | 2022-11-03 | 2022-11-03 |  | 3/14/2022 | 3/16/2022 | 3/17/2022 | 3/17/2022 | 3/18/2022 |  |  | GoP | 35980 | 35980 |  | 35600 |  |  | COA |  | 2022-08-03 | 2022-08-03 |  | 2022-10-03 | 3 days
| Supply and Delivery of Meals (Lunch) and Snacks (AM and PM) of the Program Management Team and Speaker for the conduct of Orientation to the School Sports Coordiantor on the Implementation of School Sports Club 4/18-19/22 | [19 empty] | SGOD | NO | Shopping | 2/23/2022 |  |  | 2022-04-04 | 4/4/2/22 |  | 2022-05-04 | 2022-07-04 | 2022-08-04 | 2022-08-04 | 2022-11-04 |  |  | GoP | 10000 | 10000 |  | 9890 |  |  | COA |  | 3/30/2022 | 3/30/2022 |  | 2022-01-04 | 2 days
| Supply and delivery of Project Kept (Kindergarten Education Program for Teachers ) 4- 20-22,2022 | [19 empty] | CID | NO | Shopping | 2022-07-03 |  |  | 2022-11-03 | 2022-11-03 |  | 3/14/2022 | 3/16/2022 | 3/17/2022 | 3/17/2022 | 3/18/2022 |  |  | GoP | 30000 | 30000 |  | 27000 |  |  | COA |  | 2022-08-03 | 2022-08-03 |  | 2022-10-03 | 2 days
| Supply and Delivery of Meals and Snacks for the Selected Public Schools District Supervisor , MAPEH, Coordinators, Elementary and Sec Schools Teachers for Two (2) days for the conduct of Division Virtual Seminar on Project Guitar ( on April 25-26,2022 at LRMDS | [19 empty] | CID | NO | Shopping | 2022-04-04 |  |  | 2022-11-04 | 2022-11-04 |  | 4/13/2022 | 4/19/2022 | 4/20/2022 | 4/20/2022 | 4/21/2022 |  |  | GoP | 20000 | 20000 |  | 19800 |  |  | COA |  | 2022-06-04 | 2022-06-04 |  | 2022-11-04 | 2 days
| Lease of Training Venue including Meals (Lunch) and Snacks (AM & PM) use of Facilities and Amenities with backdrop tarpaulin for the Participants and Program Management Team for One (1) day for the conduct of Orientation on the Induction Program for Newly Hired Teachers on April 12, 2022 | [19 empty] | SGOD | NO | Shopping | 2022-04-04 |  |  | 4/18/2022 | 4/18/2022 |  | 4/19/2022 | 4/20/2022 | 4/21/2022 | 4/21/2022 | 4/22/2022 |  |  | GoP | 19800 | 19800 |  | 19800 |  |  | COA |  | 2022-11-04 | 2022-11-04 |  | 4/13/2022 | 1 day
| Supply and Delivery of Meals (Lunch) and Snacks(AM&PM) for Three (3) days for the conduct of Virtual Capacity Building for Supreme Pupil Government (SPG) and Supreme Student Government (SSG) Teacher – Advisers on April 26-28, 2022 | [19 empty] | SGOD | NO | Shopping | 2022-04-04 |  |  | 2022-11-04 | 2022-11-04 |  | 4/13/2022 | 4/19/2022 | 4/20/2022 | 4/20/2022 | 4/21/2022 |  |  | GoP | 9000 | 9000 |  | 8910 |  |  | COA |  | 2022-06-04 | 2022-06-04 |  | 2022-11-04 | 3 days
| Supply and Delivery of Meals (Lunch) and Snacks(AM&PM) for One (1) day for the conduct of Capacity Building to SDRRMCS on Legal Bases governing DRRM and School Based DRRM on April 29,2022 | [19 empty] | SGOD | NO | Shopping | 2022-04-04 |  |  | 2022-11-04 | 2022-11-04 |  | 4/13/2022 | 4/19/2022 | 4/20/2022 | 4/20/2022 | 4/21/2022 |  |  | GoP | 15000 | 15000 |  | 14850 |  |  | COA |  | 2022-06-04 | 2022-06-04 |  | 2022-11-04 | 1 day
| Lease of Training Venue including Meals (Lunch) and Snacks (AM & PM) use of Facilities and Amenities for the one (1) day Orientation on the opening of Bank Account with government servicing bank | [19 empty] | OSDS | NO | Shopping | 4/18/2022 |  |  | 4/20/2022 | 4/20/2022 |  | 4/20/2022 | 4/22/2022 | 4/25/2022 | 4/25/2022 | 4/26/2022 |  |  | GoP | 12600 | 12600 |  | 12600 |  |  | COA |  | 4/13/2022 | 4/13/2022 |  | 4/18/2022 | 1 day
| Lease of Training Venue including Meals(Lunch) and Snacks (AM & PM) for the conduct of three (3) days Project DREAM (Digitized Resources in Education for Applicable Modalities) – Training for Kindergarten Teachers on the Finalization of Contextualized Storybooks for Quarters 3 and 4 on May 18-20, 2022 | [19 empty] | CID | NO | Shopping | 2022-04-04 |  |  | 2022-11-04 | 2022-11-04 |  | 4/13/2022 | 4/19/2022 | 4/20/2022 | 4/20/2022 | 4/21/2022 |  |  | GoP | 30000 | 30000 |  | 29100 |  |  | COA |  | 2022-06-04 | 2022-06-04 |  | 2022-11-04 | 3 days
| Supply and Delivery of Meals (Lunch) and Snacks (AM&PM) for the conduct of One (1) day Orientation –Training Workshop of Multigrade Teachers on the Effective Utilization of the Learning Activity Sheets on May 25, 2022 | [19 empty] | CID | NO | Shopping | 2022-04-04 |  |  | 2022-11-04 | 2022-11-04 |  | 4/13/2022 | 4/19/2022 | 4/20/2022 | 4/20/2022 | 4/21/2022 |  |  | GoP | 5700 |  | 5700 | 5320 |  |  | COA |  | 2022-06-04 | 2022-06-04 |  | 2022-11-04 | 1 day
| Supply and Delivery of Meals (Lunch) and Snacks(AM&PM) for the conduct of One (1) day Orientation –Training Workshop of Multigrade Teachers on the Effective Utilization of the Learning Activity Sheets on May 26, 2022 | [18 empty] | c | CID | NO | Shopping | 2022-04-04 |  |  | 2022-11-04 | 2022-11-04 |  | 4/13/2022 | 4/19/2022 | 4/20/2022 | 4/20/2022 | 4/21/2022 |  |  | GoP | 7500 |  | 7500 | 7000 |  |  | COA |  | 2022-06-04 | 2022-06-04 |  | 2022-11-04 | 1 day
| Lease of Training Venue including Meals(Lunch) and Snacks (AM & PM) for the conduct of Division Seminar-Workshop on Project ICOmseal Integration of Comprehensive sexuality education across learning areas | [19 empty] | CID | NO | Shopping | 4/25/2022 |  |  | 2022-04-05 | 2022-04-05 |  | 2022-05-05 | 2022-11-05 | 2022-12-05 | 2022-12-05 | 5/13/2022 |  |  | GoP | 49500 | 49500 |  | 49005 |  |  | COA |  | 4/29/2022 | 4/29/2022 |  | 2022-03-05 | 3 days
| Supply and Delivery of Meals and Snacks for the conduct of Online BEIS Data/Information | [19 empty] | SGOD | NO | Shopping | 2022-05-05 |  |  | 2022-12-05 | 2022-12-05 | [8 empty] | GoP | 9900 |  |  | 9000 |  |  | COA | [6 empty] | Cancelled Activity
| Supply and Delivery of Supplies to be used for the conduct of DRRM Executive Conference cum Planning of DepEd DRRMCAP officers and Board Members | [19 empty] | SGOD | NO | Shopping | 5/27/2022 |  |  | 2022-06-06 | 2022-06-06 |  | 2022-07-06 | 2022-09-06 | 2022-09-06 | 2022-09-06 | 2022-10-06 |  |  | GoP | 5000 |  | 5000 | 4928.5 |  |  | COA |  | 2022-01-06 | 2022-01-06 |  | 2022-02-06 | 1 day
| Repair and Maintenance of Furniture and Fixtures (Aircon Units of DO Office | [19 empty] | OSDS | NO | Shopping | 4/20/2022 |  |  | 4/25/2022 | 4/25/2022 |  | 4/28/2022 | 2022-02-05 | 2022-04-05 | 2022-04-05 | 2022-05-05 |  |  | GoP | 5700 | 5700 |  | 5700 |  |  | COA |  | 4/20/2022 | 4/20/2022 |  | 4/26/2022 | 7 days
| Supply and Delivery of 25SF Battery for the Division Office Service Vehicle (Old Commuter Van, CS-B13787 | [19 empty] | OSDS | NO | Shopping | 5/25/2022 |  |  | 5/30/2022 | 5/30/2022 |  | 5/31/2022 | 2022-02-06 | 2022-03-06 | 2022-03-06 | 2022-06-06 |  |  | GoP | 8500 | 8500 |  | 8490 |  |  | COA |  | 5/25/2022 | 5/25/2022 |  | 5/27/2022 | 3 days
| Repair.,Maintenance and Installation and Installation of Spare Parts for Division Office Service Vehicles (Old and New Commuter Van) | [19 empty] | OSDS | NO | Shopping | 4/20/2022 |  |  | 4/25/2022 | 4/25/2022 |  | 4/28/2022 | 2022-02-05 | 2022-04-05 | 2022-04-05 | 2022-05-05 |  |  | GoP | 10150 | 10150 |  | 10150 |  |  | COA |  | 4/20/2022 | 4/20/2022 |  | 4/26/2022 | 7 days
| Lease of Training Venue including Meals (Lunch) and Snacks (AM & PM) use of Facilities and Amenities for three (3) days for the TWG of Division Demo fest on Project TIME | [19 empty] | CID | NO | Shopping | 5/25/2022 |  |  | 5/30/2022 | 5/30/2022 |  | 5/31/2022 | 2022-02-06 | 2022-03-06 | 2022-03-06 | 2022-06-06 |  |  | GoP | 19500 | 19500 |  | 19461 |  |  | COA |  | 5/25/2022 | 5/25/2022 |  | 5/27/2022 | 3 days
| Supply, Delivery and Printing of Third Quarter Learning Activity Sheets in English, Math and Science | [19 empty] | CID | NO | Shopping | 2022-04-04 |  |  | 5/13/2022 | 5/13/2022 |  | 5/16/2022 | 5/18/2022 | 5/19/2022 | 5/19/2022 | 5/20/2022 |  |  | GoP | 14744 |  | 14744 | 14744 |  |  | COA |  | 2022-10-05 | 2022-10-05 |  | 2022-12-05 | 15 days
| Supply, Delivery and Printing of Fourth Quarter Learning Activity Sheets in English, Math and Science | [19 empty] | CID | NO | Shopping | 5/25/2022 |  |  | 5/30/2022 | 5/30/2022 |  | 5/31/2022 | 2022-02-06 | 2022-03-06 | 2022-03-06 | 2022-06-06 |  |  | GoP | 18325 |  | 18325 | 18325 |  |  | COA |  | 5/25/2022 | 5/25/2022 |  | 5/27/2022 | 15 days
| Supply and Delivery of Meals (Lunch) and Snacks (AM & PM) of the PMT for the conduct of Virtual Orientation and Training on Video Content and Production Editing and Other Online Platforms and Technologies on June 9-10, 2022 | [19 empty] | SGOD | NO | Shopping | 5/25/2022 |  |  | 5/30/2022 | 5/30/2022 |  | 5/31/2022 | 2022-02-06 | 2022-03-06 | 2022-03-06 | 2022-06-06 |  |  | GoP | 30000 | 30000 |  | 29750 |  |  | COA |  | 5/25/2022 | 5/25/2022 |  | 5/27/2022 | 2 days
| Supply , Delivery and Printing of PYC Bookmarks and PYC Programs for the PYC 2022 | [19 empty] | OSDS | NO | Shopping | 5/27/2022 |  |  | 2022-06-06 | 2022-06-06 |  | 2022-07-06 | 2022-09-06 | 2022-10-06 | 2022-10-06 | 6/13/2022 |  |  | GoP | 32000 |  | 32000 | 31500 |  |  | COA |  | 2022-01-06 | 2022-01-06 |  | 2022-02-06 | 3 days
| Supply and Delivery of Equipment for Breastfeeding Room. | [19 empty] | SGOD | NO | Shopping | 5/25/2022 |  |  | 5/30/2022 | 5/30/2022 |  | 5/31/2022 | 2022-02-06 | 2022-03-06 | 2022-03-06 | 2022-06-06 |  |  | GoP | 40000 | 40000 |  | 39900 |  |  | COA |  | 5/25/2022 | 5/25/2022 |  | 5/27/2022 | 7 days
| Supply , Delivery and Printing of PYC ID for Delegates ad Chairperson, Working Committee/Secretariat and Media and other External Partners/Volunteers/LGU For the PYC 2022 | [19 empty] | OSDS | NO | Shopping | 5/25/2022 |  |  | 2022-06-06 | 2022-06-06 |  | 2022-07-06 | 2022-09-06 | 2022-10-06 | 2022-10-06 | 6/13/2022 |  |  | GoP | 48135 |  | 48135 | 45728.25 |  |  | COA |  | 2022-01-06 | 2022-01-06 |  | 2022-02-06 | 1 day
| Supply and Delivery of Meals(Lunch) and Snacks (AMand PM) for the conduct of Division Career Advocacy Congress for Secondary School Guidance Counselors & Designates | [19 empty] | CID | NO | Shopping | 2022-10-06 |  |  | 6/20/2022 | 6/20/2022 |  | 6/21/2022 | 6/23/2022 | 6/24/2022 | 6/24/2022 | 6/27/2022 |  |  | GoP | 35000 | 35000 |  | 34965 |  |  | COA |  | 6/15/2022 | 6/15/2022 |  | 6/17/2022 | 1 day
| Lease of Training Venue including Meals and Snacks use of Facilities and amenities for the conduct of 2nd Quarter DMEPA 2022 | [19 empty] | SGOD | NO | Shopping | 6/20/2022 |  |  | 6/24/2022 | 6/24/2022 |  | 6/24/2022 | 6/27/2022 | 6/28/2022 | 6/28/2022 | 6/29/2022 |  |  | GoP | 20000 | 20000 |  | 19900 |  |  | COA |  | 6/21/2022 | 6/21/2022 |  | 6/22/2022 | 1 day
Total Alloted Budget of Procurement Activities
Total Contract Price of Procurement Actitvites Conducted
Total Savings (Total Alloted Budget - Total Contract Price)
0N-GOING PROCUREMENT ACTIVITIES
GoP
0
0
0
Total Alloted Budget of On-going Procurement Activities
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | ANNA MYLENE F. NATIVIDAD | [9 empty] | CYRIL C. SERADOR, PhD | [11 empty] | MARITES P. PEREZ, EdD, CESE
[21 empty] | BAC Secretariat | [9 empty] | BAC Chairperson | [11 empty] | Head of the Procuring Entity